## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Duration | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone: Project Initiation- Kick off
1.1 | Contanct and get consensous from GMs of North and Downton location | 1 | bar: WEEK 1 M
1.2 | Plan and execute Kick off meeting with Core team | 2 | bar: WEEK 1 T to WEEK 1 W
1.3 | Generate Project Documentation (Menu/ Prices / Coupons) | 3 | bar: WEEK 1 W to WEEK 1 F
2 | Milestone: Hardware Instalation
2.1 | Get quotes for tablets with the needed features from different vendors | 2 | bar: WEEK 2 M to WEEK 2 T
2.2 | Generate report and choose the best offer | 1 | bar: WEEK 2 W
2.3 | Create a Risk Plan for hardware vendor issues | 2 | bar: WEEK 2 R to WEEK 2 F
2.4 | Create contracts and SOW for vendors | 1 | bar: WEEK 3 M
2.5 | Receive and Confirm order and functionality of tablets | 10 | bar: WEEK 3 M to WEEK 4 F
2.6 | Create Plan for Tablet Storing and Charging in both locations | 2 | bar: WEEK 4 R to WEEK 4 F
2.7 | Book an electrician for consultation for wiring for terminal and ticketing system for both locations | 2 | bar: WEEK 4 R to WEEK 4 F
2.8 | Get quotes and schedule electrician to install the hardware (both locations) | 4 | bar: WEEK 5 M to WEEK 5 R
2.9 | Gather additional hardware cost data for project report | 1 | bar: WEEK 5 F
3 | Milestone : Install Software and ensure functionality
3.1 | Get quote and choose a suiting software for the tablet integration | 1 | bar: WEEK 5 F
3.2 | Schedule vendor and IT specialist meeting to provide information for the tablet software | 2 | bar: WEEK 6 M to WEEK 6 T
3.3 | Upload software and new content on all tablets and terminal | 5 | bar: WEEK 6 T to WEEK 7 M
3.4 | Ensure functionality of ordering system and pefrorm tests for terminal and tablets (both locations) | 2 | bar: WEEK 7 T to WEEK 7 W
3.5 | Integration of tablets and POS payments (3rd party software) both locations | 2 | bar: WEEK 7 R to WEEK 7 F
3.6 | Ensure ticketing system and kitchen terminal functionality | 1 | bar: WEEK 8 M
3.7 | Install add-on and coupon feature | 1 | bar: WEEK 8 T
3.8 | Create an action plan in case of software malfunction | 1 | bar: WEEK 8 W
4 | Milestone : Training
4.1 | HR meeting to ensure training resources needed | 1 | bar: WEEK 8 R
4.2 | Management meeting to introduce the proposed solution and tablets-terminal software | 1 | bar: WEEK 8 F
4.3 | Schedule training curicculum and sessions | 2 | bar: WEEK 8 F to WEEK 9 M
4.4 | Train Management for the new system | 7 | bar: WEEK 9 T to WEEK 10 W
4.5 | Train FOH and BOH staff to the new functionalities and procedures (Both locations) | 7 | bar: WEEK 9 T to WEEK 10 W
4.6 | Test functionality of ordering , accepting orders , coupons and menu by staff | 1 | bar: WEEK 10 R
4.7 | Present FOH and BOH staff the action plan in case of malfunction, receive inputs | 1 | bar: WEEK 10 F
5 | Milestone: Launch
5.1 | Perform Test run before launch for all procedures (friend and family) | 1 | bar: WEEK 11 M
5.2 | Schedule launch in a weekday to avoid excessive workload (both Locations) | 2 | bar: WEEK 11 T to WEEK 11 W
5.3 | Monitor metrics for Bar area | 2 Weeks | bar: WEEK 11 M to WEEK 12 F
5.4 | Conduct a post launch survey to asses customer satisfaction of the pilot program | 2 Weeks | bar: WEEK 11 M to WEEK 12 F

## Task Brainstorm
Task Brainstorm
Milestones | Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
1 | Milestone: Project Initiation- Kick off
1.1 | Contanct and get consensous from GMs of North and Downton location |  | 1
| Plan and schedule Kick off meeting with Core team |  | 1
1.2 | Execute Kick off meeting with Core team |  | 1
1.3 | Generate Project Documentation (Menu/ Prices / Coupons) | Get feedback from Omar and other Stakeholders | 3
2 | Milestone: Hardware
2.1 | Get quotes for tablets with the needed features from different vendors |  | 2
2.2 | Generate report and choose the best offer |  | 1
2.3 | Create a Risk Plan for hardware vendor issues |  | 2
2.4 | Create contracts and SOW for vendors |  | 1
2.5 | Receive and Confirm order and functionality of tablets (use old untill new arrive) | Consult GMs for appropriate Time due to delays | 10
2.6 | Create Plan for Tablet Storing and Charging in both locations |  | 2
2.7 | Book an electrician for consultation for wiring for terminal and ticketing system for both locations | Consult GMs for appropriate Time | 2
2.8 | Get quotes and schedule electrician to install the hardware (both locations) | Consult GMs for appropriate Time | 4
2.9 | Gather additional hardware cost data for project report |  | 1
3 | Milestone : Install Software and ensure functionality
3.1 | Get quote and choose a suiting software for the tablet integration |  | 1
3.2 | Schedule vendor and IT specialist meeting to provide information for the tablet software |  | 2
3.3 | Upload software and new content on all tablets and terminal |  | 5
3.4 | Ensure functionality of ordering system and pefrorm tests for terminal and tablets (both locations) |  | 2
3.5 | Integration of tablets and POS payments (3rd party software) both locations |  | 2
3.6 | Ensure ticketing system and kitchen terminal functionality |  | 1
3.7 | Install add-on and coupon feature |  | 1
3.8 | Create an action plan in case of software malfunction |  | 1
4 | Milestone : Training
4.1 | HR meeting to ensure training resources needed |  | 1
4.2 | Management meeting to introduce the proposed solution and tablets-terminal software |  | 1
4.3 | Schedule training curicculum and sessions |  | 2
4.4 | Train Management for the new system |  | 7
4.5 | Train FOH and BOH staff to the new functionalities and procedures (Both locations) |  | 7
4.6 | Test functionality of ordering , accepting orders , coupons and menu by staff |  | 1
4.7 | Present FOH and BOH staff the action plan in case of malfunction, receive inputs |  | 1
5 | Milestone: Launch
5.1 | Perform Test run before launch for all procedures (friend and family) |  | 1
5.2 | Schedule launch in a weekday to avoid excessive workload (Launch Date for Both Locations) |  | 2
5.3 | Monitor metrics for Bar area |  | 2 Weeks
5.4 | Conduct a post launch survey to asses customer satisfaction of the pilot program |  | 2 Weeks

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Service | Average Ticket Time 15 minutes max | How quickly did you recieve your food once ordered? | Time it took for food to be served | FALSE
Ordering | Ordering and sending order 5 mins or less | How seamless was the ordering process | Time it took to place order | FALSE
Check out | Check out time 1 min or less | How seamless was the checkout process | Time it took to check out | FALSE
Order Accuracy | Order Accuracy 98% | Did you experience and issues with your order? | Yes or No measures accuracy of order. | FALSE
Tablet Use | Down Time for Tabs is less than 5% | Can be tracked by if tablet was used or not | Waiter Order or tablet Order | FALSE
Wait time for tables | Wait time less than 10 minutes | How long did you wait before you were seated? | Time it took to be seated | FALSE
Customer Experience | Customer Experience being 90% or higher | Did the customer enjoy the experience of using the tablet | EOM Survey | FALSE
Customer Experience | Tablet Ease of use | Did the customer understand how to use the tablet | Ease of Use | FALSE
Customer Experience | Staff Support | Did the waitstaff offer to assist the customer with the tablet | Customer satisfaction and team knowledge | FALSE
Customer Experience | Retention | Will the customer return? | Customer retention and growth | FALSE
Customer Experience | Recommendation | Will the custmer recommend the restaurant | Customer Reccomendation and growth | FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average Ticket Time 15 minutes max | How quickly did you recieve your food once ordered? | Time it took for food to be served | How quickly did you recieve your food once ordered? | Multiple choice | 5-10 minutes | 10-15 minutes | 15 to 20 minutes | 20 to 25 Minutes | 25 or more minutes
Complete and Send time 5 min or less | How seamless was the ordering process | Time it took to send order | Did you experience any issues completing the order (more than 5 min) | Yes/No | Yes | No
Complete and Send time 1 min or less | How seamless was the checkout process | Time it took to pay and get confirmation | Did you experience any issues completing checkout and payment (more than 1 min) | Yes/No | Yes | No
Order Accuracy 98% | Did you experience and issues with your order? | Yes or No measures accuracy of order. | Did you experience any issues with your food or drinks? | Open-ended | Open Ended
Down Time for Tabs is less than 5% | Can be tracked by if tablet was used or not | Server order or Tablet Order | Quantitative Data retreived by terminal
Wait time less than 10 minutes | How long did you wait before you were seated? | Time it took to be seated | How long did you wait before you were seated? | Multiple choice | 1-5 minutes | 5 - 10 minutes | 10 - 15 minutes | 15+ Minutes
Customer Experience being 90% or higher | Did the customer enjoy the experience of using the tablet | EOM Survey | On a scale of 1 to 5 where 5 is the best, how would you rate your dining experience (tablet order) | Scaled | 1 | 2 | 3 | 4 | 5
Tablet confusion | Did the customer understand how to use the tablet | Scale | How would you rate the tablet ordering system in terms of ease of use | Scaled | 1 | 2 | 3 | 4 | 5
Waitstaff Support | Did the waitstaff offer to assist the customer with the tablet | Customer satisfaction and team knowledge | Did a member of our team offer to explain tablet functionality? | True/False | TRUE | FALSE
Return Service | Will the customer return? (Rentention) | Customer retention and growth | On a scale of 1 to 5 (5 is max , 1 is min) Would you come eat with us again? | Scaled | 1 | 2 | 3 | 4 | 5
| Will the customer suggest to a friend? (Recomendation) | Recommendation | On a scale of 1 to 5 (5 is max , 1 is min). Would you recommend the restaurant to a friend | Scaled | 1 | 2 | 3 | 4 | 5
Rating Scale
1: Very Satisfied
2: Somewhat satisfied
3: Neither satisfied nor dissatisfied
4: Somewhat dissatisfied
5: Very dissatisfied